## 第1次迭代
QR Check-ins 第1次迭代计划 | [9 empty] | Gantt Chart © 2012-2014 by Vertex42.com
SYSU
| Project Lead: |  | 陆莹 |  | Completed Task
| Project Start Date: |  | 2014-05-12 |  | Incomplete Task
| Today's Date: |  | 2014-05-12 |  | Artifact / Milestone* | time axis 2014-05-12 to 2014-07-06
| Display Week: |  | 1 | [6 empty] | 2014-05-12: Week 1; 2014-05-19: Week 2; 2014-05-26: Week 3; 2014-06-02: Week 4; 2014-06-09: Week 5; 2014-06-16: Week 6; 2014-06-23: Week 7; 2014-06-30: Week 8
[10 empty] | 2014-05-12 | [6 empty] | 2014-05-19 | [6 empty] | 2014-05-26 | [6 empty] | 2014-06-02 | [6 empty] | 2014-06-09 | [6 empty] | 2014-06-16 | [6 empty] | 2014-06-23 | [6 empty] | 2014-06-30
WBS | Task | Lead | Start | End | Cal Days | % Done | Work Days | Days Done | Days Left | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1 | 制定迭代计划 | 陆莹 | 2014-05-12 | 2014-05-12 | 1 |  | 1 | bar: 2014-05-12 to 2014-07-06
1.1 | 迭代计划会议 | 陆莹 | 2014-05-12 | 2014-05-12 | 1 | 100% | 1 | 1 | 0 | bar: 2014-05-12
1.2 | 迭代计划书 | 陆莹 | 2014-05-12 | 2014-05-12 | 1 | 100% | 1 | 1 | 0 | bar: 2014-05-12
2 | 敏捷建模 |  | 2014-05-13 | 2014-05-14 | 2 |  | 2 | bar: 2014-05-12 to 2014-07-06
2.1 | 用例模型 | 黄永智 | 2014-05-13 | 2014-05-13 | 1 | 100% | 1 | 1 | 0 | bar: 2014-05-12 to 2014-05-13
2.2 | 补充说明书 | 郭钊宏 | 2014-05-14 | 2014-05-14 | 1 | 100% | 1 | 1 | 0 | bar: 2014-05-12; 2014-05-14
2.3 | 术语表 | 袁德伦 | 2014-05-14 | 2014-05-14 | 1 | 100% | 1 | 1 | 0 | bar: 2014-05-12; 2014-05-14
3 | 系统设计 |  | 2014-05-15 | 2014-05-16 | 2 |  | 2 | bar: 2014-05-12 to 2014-07-06
3.1 | 模型分析 | 蔡浩忠 | 2014-05-15 | 2014-05-15 | 1 | 100% | 1 | 1 | 0 | bar: 2014-05-12; 2014-05-15
3.2 | 用例设计 |  | 2014-05-15 | 2014-05-15 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-15
3.3 | 系统逻辑架构模型 |  | 2014-05-16 | 2014-05-16 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-16
3.4 | 数据库设计与部署设计 |  | 2014-05-16 | 2014-05-16 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-16
4 | 开发构造 |  | 2014-05-17 | 2014-05-22 | 6 |  | 4 | bar: 2014-05-12 to 2014-07-06
4.1 | 搭建框架 |  | 2014-05-17 | 2014-05-18 | 2 | 0% | 0 | 0 | 2 | bar: 2014-05-12; 2014-05-17 to 2014-05-18
4.2 | 二维码生成和识别 |  | 2014-05-19 | 2014-05-21 | 3 | 0% | 3 | 0 | 3 | bar: 2014-05-12; 2014-05-19 to 2014-05-21
4.3 | 后台和数据库 |  | 2014-05-19 | 2014-05-21 | 3 | 0% | 3 | 0 | 3 | bar: 2014-05-12; 2014-05-19 to 2014-05-21
4.4 | 前后端链接 |  | 2014-05-22 | 2014-05-22 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-22
4.5 | 单元测试 |  | 2014-05-19 | 2014-05-22 | 4 | 0% | 4 | 0 | 4 | bar: 2014-05-12; 2014-05-19 to 2014-05-22
5 | 阶段性发布 |  | 2014-05-23 | 2014-05-25 | 3 |  | 1 | bar: 2014-05-12 to 2014-07-06
5.1 | 代码检入并集成 |  | 2014-05-23 | 2014-05-23 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-23
5.2 | 验收测试 |  | 2014-05-24 | 2014-05-24 | 1 | 0% | 0 | 0 | 1 | bar: 2014-05-12; 2014-05-24
5.3 | 局部产品发布* |  | 2014-05-25 | 2014-05-25 | 1 | 0% | 0 | 0 | 1 | bar: 2014-05-12; 2014-05-25
6 | 需求工作会 |  | 2014-05-26 | 2014-05-26 | 1 |  | 1 | bar: 2014-05-12 to 2014-07-06
6.1 | 工作进度复查 |  | 2014-05-26 | 2014-05-26 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-26
6.2 | 下一次迭代计划 |  | 2014-05-26 | 2014-05-26 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-26
7 | 阶段性总结 |  | 2014-05-27 | 2014-05-27 | 1 |  | 1 | bar: 2014-05-12 to 2014-07-06
7.1 | 总结与改进 |  | 2014-05-27 | 2014-05-27 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12; 2014-05-27
t
t
TEMPLATE ROWS | bar: 2014-05-12
See the Help worksheet for information about using template rows. | bar: 2014-05-12
1 | [ Task Category (label only) ] | bar: 2014-05-12
2 | [ Task Category (summary) ] |  | 2014-05-12 | 2014-05-12 | 1 |  | 1 | bar: 2014-05-12 to 2014-07-06
2.1 | [ Level 2 Task ] |  | 2014-05-12 | 2014-05-12 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12
2.1.1 | . [ Level 3 Task ] |  | 2014-05-12 | 2014-05-12 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12
2.1.1.1 | . . [ Level 4 Task ] |  | 2014-05-12 | 2014-05-12 | 1 | 0% | 1 | 0 | 1 | bar: 2014-05-12
Formulas:
陆莹 = MIN([陆莹, row below]:D11)
陆莹 = [陆莹, row above]
Note on B5: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on A8: Work Breakdown Structure: Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, Level 3: 1.1.1, 1.1.2, The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B8: Task: Enter the name of each task and sub-task. Use spaces to indent sub-tasks.
Note on C8: Task Lead Enter the name of the Task Lead in this column.
Note on D8: Task Start Date: You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E8: End Date: Calculated based on the Start Date and the duration of the task.
Note on F8: Duration: The duration is the number of calendar days for the given task.
Note on G8: Percent Complete: Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H8: Work Days: Work Days exclude Saturday and Sunday. The Pro version allows you to use this column as an input.
Note on I8: Calendar Days Complete: This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer. Note: This column is required, but may be hidden prior to printing.
Note on J8: Calendar Days Remaining: This column is calculated by subtracting the Days Complete from the Duration. Note: This column is required, but may be hidden prior to printing.

## Help
HELP |  | © 2012-2014 Vertex42 LLC
| If this Help worksheet and the info on Vertex42's website does not answer your questions: | Contact Vertex42
Intro
This Gantt Chart spreadsheet makes creating a project schedule very easy. You only need to know some basic spreadsheet operations to make this gantt chart work for you, such as how to insert, delete, copy and paste entire rows.
Be sure to read the Getting Started Tips below. It would also be a good idea to watch the demo videos on Vertex42.com. The demo videos are of the Excel version, but much of the information is applicable to the Google Sheets version as well.
Watch the Demo Videos on Vertex42.com
The Share settings for this spreadsheet must always be set to "Private"
See the TermsOfUse worksheet for more information about how you may and may not share this Gantt Chart Template.
Getting Started Tips
- | Input cells have a light green background. | Input Cell
- | [ Bracketed Text ] is also meant to be edited, like the project title and task descriptions.
- | Some of the labels include cell notes to provide extra help information. | Label
- | The Project Start Date determines the first week shown in the gantt chart.
- | To adjust the range of dates shown in the gantt chart, change the Display Week.
- | The red line in the gantt chart represents the date in the Today's Date cell. You can enter Today's Date manually or use the formula =TODAY()
- | To insert a new task, insert a new row, then copy/paste an existing row from the selection of Template Rows at the bottom of the worksheet.
- | Edit the Holidays worksheet to choose which dates you want to exclude from Work Days.
Cell Color Key
Input Cell | :: Indicates which set of inputs to use
Completed Task | :: In the Gantt chart, indicates the completed portion of the task
Incomplete Task | :: In the Gantt chart, indicates the incomplete portion of the task
Using the Template Rows and Choosing a WBS Level
Inserting New Tasks
1. Insert a new blank row where you want the new task to be
2. Copy the entire row you want to use from the set of template rows
3. Paste the row you copied on top of the blank row you just inserted
4. Copy and paste the WBS cell separately, based on the level (1, 2.1, 3.2.1, 4.3.2.1)
- When inserting new rows, you must copy and paste an entire row, because the cells of the Gantt chart area are formulas.
Changing the WBS Level in the WBS Column
- The WBS numbering uses a different formula for each level, but the formula does not reference any other cell in the row. So, you can copy and paste just the WBS cell that you want to use.
- If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter them if you need to.
- You can indent the task description for sub-tasks by entering spaces (until Google decides to add an indent option).
Category Tasks
- You can use tasks that are just labels, but it can be even more useful for a category task to display the minimum Start date and maximum End date of its sub tasks. This can be done using =MIN(range_of_startdates) and =MAX(range_of_enddates). An example template row is provided, but you will need to update the MIN() and MAX() formulas.
Creating Task Dependencies
- You can enter the Start date manually, or define task dependecies using a formula. Below are the most common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
- Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
- For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
- This formula is very simple: =enddate+1
- For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3 )+1
E. | Set the Start date to a number of days before or after another date.
- This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
FAQs
Q: | What is the best way to Print?
First, select all of the rows you want to print. Then, in the Print Settings, choose "Selection" and check "No Gridlines". Fit to width and print in landscape.
You also may want to hide the Days Done, Days Left, and Color columns prior to printing.
Q: | How do I only show Monday-Friday in the chart area?
You can hide the columns that show the weekends.
Q: | How do I print the entire range of dates for my project?
You would first need to add more columns to the displayed chart area. You can insert more columns to the right of the chart area and then copy and paste columns (7 at a time) to extend the display.
Note: The more columns you add to the right of the Gantt chart, the slower the recalculation speed will be, because of the number of additional formulas.
Q: | How do I calculate the %Complete for a Summary task?
The %Complete for a summary task can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work days and "complete" is a reference to the %complete for each of the subtasks.
=ARRAYFORMULA( SUMPRODUCT( workdays, complete ) / SUM ( workdays ) )
Q: | The Start date, End date, or %Complete for a Level 1 task is wrong. How do I fix it?
When using =MIN(), =MAX(), and =SUMPRODUCT(), it is easy for the references to get messed up if you move rows around or insert new rows. You should verify and fix these formulas if they are not referencing the correct ranges.
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the cells that are messed up.
Note on C1: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on C16: This is an example comment.

## TermsOfUse
Terms of Use
Gantt Chart Template for Google Sheets
© 2012-2014 Vertex42 LLC. All rights reserved.
This template is considered a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
The Share Settings for this spreadsheet must always be set to "Private"
Only the person or organization who purchased this spreadsheet from Vertex42.com may share it with other team members. If some team members are in a different organization, they must purchase their own license to use this template for other projects.
Not for Resale or Public Sharing
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
Limited Private Sharing
Provided that you observe the above terms, you may share your edited version of this template *privately* with those specific people who **require** access to it within your immediate family, organization, or company.
* "Privately" means only accessible to those few people who you expressively give permission to view or edit your file. It is your responsibility to ensure that adequate security measures are used so that your file is not available to the public.
** Examples of acceptable private sharing with people who "require access" may include (a) sharing a budget spreadsheet with a spouse, (b) sharing a project schedule with your project team, or (c) sharing a timesheet with your employee or manager.
See the following page on Vertex42.com for the complete license agreement and examples of other allowed uses:
http://www.vertex42.com/licensing/EULA_privateuse.html
Disclaimer
Vertex42 LLC makes no guarantee or representations about this template, or the accuracy or completeness of the content contained within this template.
Vertex42 LLC encourages you to seek the aid of a qualified professional before making decisions regarding health, financial, or legal issues.
Note on A4: No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Some states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.

## © (hidden)
Gantt Chart Template
© 2012-2014 Vertex42 LLC
Please note the Terms Of Use
http://www.vertex42.com/licensing/EULA_privateuse.html